### Project: "Nimbus CRM Platform"

Type: Project
Start date: July 15, 2026
Expected end date: January 15, 2027 (6-month build)
Budget: ₹25,00,000
Currency: ₹ (INR)
Description: Building a B2B CRM SaaS product for SMBs.

#### Timeline / Phases

| Phase | Dates | Focus |
| --- | --- | --- |
| Phase 1: Foundation | Jul 15 – Aug 31, 2026 | Auth, DB schema, core API |
| Phase 2: Core Features | Sep 1 – Nov 30, 2026 | CRM modules, dashboards |
| Phase 3: Polish & Launch | Dec 1, 2026 – Jan 15, 2027 | QA, performance, launch prep |

#### Departments (with allocated budgets)

| Department | Budget |
| --- | --- |
| Engineering | ₹12,00,000 |
| Design | ₹3,50,000 |
| Marketing | ₹4,00,000 |
| Sales & Support | ₹2,50,000 |
| Operations | ₹2,00,000 |
| Total allocated | ₹24,00,000 (₹1,00,000 unallocated buffer) |

#### Team

| Name | Role | Department(s) | Monthly Cost |
| --- | --- | --- | --- |
| You | OWNER | — | — |
| Rohan Mehta | CO_ADMIN (granted expenses.approve, revenue.edit) | — | ₹1,50,000 |
| Ananya Iyer | MANAGER | Engineering | ₹1,40,000 |
| Karan Bhatt | CO_MANAGER | Engineering | ₹1,10,000 |
| Sneha Reddy | MANAGER | Design | ₹95,000 |
| Vikram Nair | MEMBER | Engineering | ₹85,000 |
| Meera Joshi | MEMBER | Engineering | ₹80,000 |
| Arjun Kapoor | MEMBER | Design | ₹70,000 |
| Divya Menon | MEMBER | Marketing, Sales & Support | ₹65,000 |

#### Tasks

Engineering / Phase 1 (Jul 15 – Aug 31):

- "Set up Postgres schema + Prisma models" — DONE — Vikram

- "Implement JWT auth + refresh tokens" — DONE — Meera

- "Build tenant isolation middleware" — IN_PROGRESS — Vikram

- "Write API rate-limiting" — TODO — Meera

Engineering / Phase 2 (Sep 1 – Nov 30):

- "Contact management module" — IN_PROGRESS — Vikram, Meera (multi-assignee)

- "Deal pipeline kanban view" — TODO — Meera

Design (dept-level, no phase):

- "Design system: color tokens + components" — DONE — Arjun

- "Dashboard high-fidelity mockups" — IN_PROGRESS — Arjun

Marketing (dept-level, no phase):

- "Landing page copy + SEO brief" — TODO — Divya

#### Milestones

| Milestone | Status | Due date |
| --- | --- | --- |
| MVP Auth Complete | ACHIEVED | Aug 31, 2026 |
| Core CRM Beta | IN_PROGRESS | Nov 30, 2026 |
| Public Launch | UPCOMING | Jan 15, 2027 |

#### Income entries

| Source | Type | Expected | Received | Status | Date |
| --- | --- | --- | --- | --- | --- |
| Sequoia Seed Round | INVESTMENT | ₹15,00,000 | ₹15,00,000 | RECEIVED | Jul 20, 2026 |
| Acme Corp — Pilot deal | CLIENT_PAYMENT | ₹2,00,000 | ₹2,00,000 | RECEIVED | Aug 5, 2026 |
| Globex Inc — Pilot deal | CLIENT_PAYMENT | ₹1,50,000 | ₹75,000 | PARTIAL | Sep 10, 2026 |
| TechStars accelerator grant | GRANT | ₹5,00,000 | ₹0 | EXPECTED | Oct 1, 2026 |
| Local dev meetup sponsorship | SPONSORSHIP | ₹50,000 | ₹50,000 | RECEIVED | Aug 15, 2026 |
| Open-source fund donation | DONATION | ₹25,000 | ₹0 | EXPECTED | Nov 1, 2026 |
| Subscription revenue (early adopters) | REVENUE | ₹1,20,000 | ₹60,000 | PARTIAL | Dec 1, 2026 |
| Misc — swag store | OTHER | ₹10,000 | ₹10,000 | RECEIVED | Sep 20, 2026 |

Pending Receivables at any snapshot ≈ ₹5,60,000 (Grant + Donation + partial remainders).

#### Expense requests

| Description | Category | Dept | Amount | Requested by | Status | Date |
| --- | --- | --- | --- | --- | --- | --- |
| AWS infra — first month | TOOLS | Engineering | ₹45,000 | Vikram | PAID | Jul 31, 2026 |
| Figma team seats | TOOLS | Design | ₹18,000 | Arjun | PAID | Jul 25, 2026 |
| Contractor — DB migration help | OPERATIONS | Engineering | ₹60,000 | Ananya | APPROVED, unpaid (payable) | Aug 20, 2026 |
| Google Ads campaign | MARKETING | Marketing | ₹80,000 | Divya | PENDING_APPROVAL | Sep 5, 2026 |
| Team offsite | OPERATIONS | — | ₹1,20,000 | You (Owner) | PENDING_APPROVAL | Oct 15, 2026 |
| Extra freelance designer | SALARY | Design | ₹40,000 | Sneha | REJECTED — "Budget already tight this quarter, revisit next sprint" | Sep 12, 2026 |
| Conference tickets | EVENT | Marketing | ₹25,000 | Divya | APPROVED, PARTIALLY_PAID (₹10,000 paid) | Nov 10, 2026 |